Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 28 September 2026 |
| --- | --- |
| Team ID | SWTID-2026-6339 |
| Project Name | AI BlogNest |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup & Authentication | USN-1 | As a user, I can register with my name, email and password (min 6 characters). | 3 | High |  |
| Sprint-1 |  | USN-2 | As a user, my password is hashed and duplicate emails are rejected. | 2 | High |  |
| Sprint-1 |  | USN-3 | As a user, I can log in and receive a JWT token (valid 7 days). | 3 | High |  |
| Sprint-1 |  | USN-4 | As a user, I can view my profile using my token. | 2 | Medium |  |
| Sprint-1 |  | USN-5 | As a developer, protected routes verify the JWT (auth middleware). | 3 | High |  |
| Sprint-1 |  | USN-6 | As a developer, I set up Express, MongoDB connection and the central error handler. | 4 | High |  |
| Sprint-1 |  | USN-7 | As a developer, request bodies are validated with express-validator. | 2 | High |  |
| Sprint-1 |  | USN-8 | As a developer, a health-check route confirms the API is running. | 1 | Low |  |
| Sprint-2 | Blog Management | USN-9 | As a user, I can create a blog with title, content and category. | 3 | High |  |
| Sprint-2 |  | USN-10 | As a reader, I can view all blogs, latest first. | 2 | High |  |
| Sprint-2 |  | USN-11 | As a reader, I can open a single blog by ID. | 2 | High |  |
| Sprint-2 |  | USN-12 | As a user, I can update my own blog. | 3 | High |  |
| Sprint-2 |  | USN-13 | As a user, I can delete my own blog. | 2 | High |  |
| Sprint-2 | Comments | USN-14 | As a user, I can add a comment to a blog. | 3 | High |  |
| Sprint-2 |  | USN-15 | As a reader, I can view all comments of a blog. | 2 | Medium |  |
| Sprint-2 |  | USN-16 | As a user, I can edit my own comment. | 2 | Medium |  |
| Sprint-2 |  | USN-17 | As a user, I can delete my own comment. | 1 | Medium |  |
| Sprint-3 | AI Content Tools | USN-18 | As a user, I can generate a blog from a topic using Gemini and save it. | 5 | High |  |
| Sprint-3 |  | USN-19 | As a user, the category is detected from the topic when I do not provide one. | 2 | Medium |  |
| Sprint-3 |  | USN-20 | As a user, AI output is cleaned of markdown symbols. | 2 | Medium |  |
| Sprint-3 |  | USN-21 | As a user, I can get a short summary of any blog content. | 3 | High |  |
| Sprint-3 |  | USN-22 | As a developer, the Gemini service handles API key, model selection and errors. | 3 | High |  |
| Sprint-3 | AI Chatbot | USN-23 | As a user, I can send a message to the chatbot and get a reply using the last 20 messages as context. | 5 | High |  |
| Sprint-4 | AI Chatbot | USN-24 | As a user, I can view my saved chat history. | 2 | Medium |  |
| Sprint-4 |  | USN-25 | As a user, I can clear my chat history. | 1 | Medium |  |
| Sprint-4 |  | USN-26 | As a user, my conversation is stored per user in MongoDB. | 3 | High |  |
| Sprint-4 | Testing & Documentation | USN-27 | As a tester, I have a Thunder Client / Postman collection for all endpoints. | 3 | Medium |  |
| Sprint-4 |  | USN-28 | As a developer, the README documents setup and endpoints. | 2 | Low |  |
| Sprint-4 |  | USN-29 | As a team, we run UAT and fix reported bugs. | 5 | High |  |
| Sprint-4 |  | USN-30 | As a team, we prepare environment configuration for deployment. | 4 | Medium |  |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 07 Sep 2026 | 12 Sep 2026 |  |  |
| Sprint-2 | 20 | 6 Days | 14 Sep 2026 | 19 Sep 2026 |  |  |
| Sprint-3 | 20 | 6 Days | 21 Sep 2026 | 26 Sep 2026 |  |  |
| Sprint-4 | 20 | 6 Days | 28 Sep 2026 | 03 Oct 2026 |  |  |

Velocity:

The team plans 4 sprints of 6 days each with a velocity of 20 story points per sprint (80 points in total). Average velocity (AV) per day = velocity / sprint duration = 20 / 6 = 3.33 story points per day.

Burndown Chart:

A burn down chart shows the work left to do against time. The chart above is the ideal plan for AI BlogNest: 80 story points falling to zero over 24 working days. Record the actual points completed at the end of each sprint in the tracker above and plot them against this line.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts